## Sheet1
Northern Gas Networks Sustainable Procurement Action Plan
| Key Targets | Main Actions to achieve Targets | Target Success Criteria | Target Completion Date | Lead Accountability | Priority H (high)/M (medium) /L (low)
Objective 1
Resilient Supply Chain | 1.1 Train the Procurement and Commercial team on Achilles and how to track critical suppliers | Engage with Achilles UVDB and arrange a training session by the end of May 2020 | Training session delivered by Achilles UVDB, attendance noted and all attendees competent users of Achilles | 2020-06-01 | MN (Maija Narimanidze) | M
| 1.2 Make Sustainable Procurement a gateway question at the PQQ stage | Review current PQQ and sustainability questions and agree % gateway that is realistic | PQQ template updated and rolled out to the team | 2020-06-01 | MN | H
| 1.3 Map our Supply Chain | Explore collaboration opportunities - engage with the Head of Procurement from Leeds Beckett University by the end of May 2020 Explore online tools or develop supply chain mapping questionnaires | Supply Chain mapped at least at Tier 2 | Critical Supply Chain - Dec 2020 80% Contracted Supply Chain - Dec 2021 | MN | M
Objective 2
Social Sustainability | 2.1 Host 'Meet the Buyer' event | Engage with external business intermediaries by the end of May 2020 Advertise the event via Linked In and other forms of social media, and NGN's procurement page Procurement team to develop content in collaboration with the Stakeholder team Host at least two events by the event by December 2020 - TO BE REVIEWED DUE TO COVID-19 | All procurement categories involved 90% of positive feedback from attendees Evidence of improved supplier engagement from local suppliers | Dec-20 - TO BE REVIEWED DUE TO COVID-19 | MN to lead with the support and involvement of all Procurement team | H
| 2.2 Supplier Code of Conduct | Create a set of standards and behaviours that we expect from our Supply Chain | Code of Conduct developed and rolled out to critical Supply Chain and included in the PQQ for all new contracts | 2020-05-01 | MN and LG (Lisa Gadsby) | H
| 2.3 Sustainability forum for existing Supply Chain | Send Expression of Interest to incumbent suppliers by the end of June 2020 | 90% positive feedback from attendees Minutes noted and circulated | Dec-20 - TO BE REVIEWED DUE TO COVID-19 | MN | M
| 2.4 Simplify the language of tender documents | Engage with business intermediaries and Leeds Beckett University for best practice by the end of May 2020 Update current procurement templates by simplifying the language to make NGN more accessible for SMEs | Procurement templates updated, corporate language simplified, examples and guidance provided for SMEs Evidence of more local SMEs bidding for contracts. | 2020-06-01 | MN | H
| 2.5 Aim to increase the level of expenditure and a number of contracts awarded to SMEs by making NGN more accessible to SMEs, where possible | Update Procurement Policy by adding a requirement to obtain at least one quote from a local SME for all below threshold tenders by May 2020 Assist SMEs in bidding for contracts with NGN, i.e. Meet the Buyer Event, reviewing tender documents and simplifying the language | Increase in the volume of contracts being awarded to SMEs and overall engagement for below threshold tenders Annual SME spend statistics produced showing incremental increase in expenditure with SMEs | 2023-03-01 | MN | M
Objective 3
Environmental Sustainability | 3.1 Hold a workshop with DSPs and other key suppliers to present our environmental requirements and provide guidance on how to meet these requirements | Engage with the Environment Team by the end of March 2020 to agree on an indicative date. Hold a workshop for suppliers to identify Environmental Action Plan requirements, where they fit in, what they can and must do, and provide basic environmental information and tools. | All DSPs and 50% of other invited suppliers attended, 90% positive feedback received Environmental data submissions received from 90% of non-DSP suppliers who attended workshop | Dec-20 - TO BE REVIEWED DUE TO COVID-19 | Environment with the support of MN | M
| 3.2 Ensure that at least 80% of our supply chain meet our environmental requirements | Hold supplier workshops with the Environment team Embed environmental requirements in Supplier Code of Conduct Develop and apply methods for measuring performance against the environmental targets Engage with Achilles for latest supply chain sustainability advice | Hold annual supply chain environment and sustainability workshop throughout RIIO-2 At least 80% of our supply chain compliant with Supplier Code of Conduct by end RIIO-2, including providing annual environmental performance data Establish supply chain 'sustainability league' to measure and compare our suppliers' environmental performance Include environmental and sustainability performance as a standing agenda item for all supplier contract performance meetings Complete supply chain carbon footprint based on provided data Minimum annual meeting with Achilles to discuss supply chain sustainability improvement | 2026-04-01 | Environment with the support of MN | M
| 3.3 Aim to achieve sustainable and innovative procurement solutions | Share Procurement Programme with the Innovation Team Attend Innovation stand up meeting and Think Tank to identify opportunities to collaborate | Minimum of 1 joint Procurement and Innovation collaborative project per year | Ongoing | MN, LG and Innovation | L
| 3.4 Share best practice with other Utilities | Collaborate with Yorkshire Water, and share learning via ENA cross GDN Environment group | Utilise learning from collaboration to improve sustainability on at least one procurement exercise per year Share minimum of three sustainable procurement case studies from our own experience and activities per year with other utilities | Ongoing | MN and Environment | M
| 3.5 Eliminate single use plastics | Assess the supply chain for single use plastics and create action plans to replace them with suitable non-single use items or more sustainable single use items where this isn't possible | No single use plastics in depots and offices | 2026-04-01 | Environment with the support of MN | H
| 3.6 Reduce our vehicle carbon footprint | Renew our company cars so that 100% of our cars are ultra-low emission or hybrid Renew our commercial fleet so that at least 25% of our commercial vans are ultra-low emission Install electric vehicle charging infrastructure across all of our offices and depots | At least 50% of our total vehicle fleet are ultra low emission or hybrid, 250 diesel vehicles removed from our fleet | 2026-04-01 | Fleet Manager with the support and involvement of Procurement team | H
Objective 4
Internal Culture | 4.1 Achieve CIPS Corporate Ethical Mark | Register the Procurement team for training by the end of May 2020 Monitor progress and assist the team, where required | All team completed CIPS 2-hours e-learning package Commercial Director signed the CIPS Statement of Commitment | 2021-03-01 | MN and all Procurement team | M
| 4.2 Present the Strategy internally | Hold a number of workshops with key stakeholders | Key stakeholders attended, 90% of positive feedback received | Aug-20 - TO BE REVIEWED DUE TO COVID-19 | MN | H
| 4.3 Promote the importance of Sustainable Procurement | Publish blogs and posts on Yammer Produce and share Sustainable Procurement Dashboard | Communication published on a quarterly basis | Ongoing | MN | M
| 4.4 Consider sustainability at the procurement strategy stage | Review and update NGN's Procurement Strategy Form Discuss the possibility of embedding environmental criteria at the RFP stage with the Environment team | Procurement Strategy Form updated - sustainability question reviewed An applicable tender is identified and environmental criteria used at the RFP stage (minimum 1 tender per year) | 2021-03-01 | MN and Environment | M